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Project Memorandum 

Monterey Accelerated Research System (MARS) Project
To:
Michelle Brown (CSLC), Deirdre Hall (MBNMS)
From:
Jenny Slaughter, Aspen Environmental Monitor
Date:
March 6, 2006
Subject:
Daily Monitoring Log 
Horizontal Directional Drill (HDD) Phase Cable Installation
CSLC/MBNMS Aspen Environmental Monitor (EM):  Jenny Slaughter.  

Environmental Training

The HDD contractor, Environmental Crossings Inc. (ECI), the CSLC/MBNMS Aspen Environmental Monitor (EM), and representatives from MBARI and MBNMS attended an Environmental Training to review project compliance requirements and permit conditions.

Summary of Activity:

Aspen EM, Jenny Slaughter, was on site Monday at the HDD location to monitor construction activities.  Weather was partly cloudy.
Construction activity at the HDD site on the MBARI property on Sandholdt road consisted of the mobilization of construction equipment and materials.  Construction hours are planned for daylight hours (between 7:00 am- 7:00 pm) seven days a week.  The County will be notified if the working hours are extended.  Crews expect to begin drilling operations on Wednesday or Thursday of this week.
1. Large equipment including the HDD bore machine, mud recycler, pump trailer, and operations trailer were mobilized to the project site.  
2. Construction crews identified a problem with the existing survey data for the bore path and a survey team was brought in to re-shoot the area.  

3. A small area was graded for the bore machine pad during the day (see Figure 1).  A concrete anchor will be poured in this location for the bore machine.

4. Crews began to install silt fencing and hay bales surrounding the locations where equipment will be staged (see Figure 2).

5. The CSLC/MBNMS Aspen EM documented pre-construction conditions of the work site by taking photographs.

Environmental Compliance Activities

1. All crew personnel attended the Environmental Training this morning at the MBARI building. 

2. The CSLC/MBNMS Aspen EM and the on-site MBARI representative reviewed project documents and permit requirements.  The CSLC/MBNMS Aspen EM reminded the contractor to maintain copies of all permits and required plans on site through the duration of the project.  

3. The bore machine was unloaded from the truck and tracked across the Moss Landing Bridge, to comply with County permit requirements for weight limitations on the bridge which is currently under construction.
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Figure 1: The graded area will be partially excavated for the placement of the concrete anchor for the bore machine.
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Figure 2: Crews installed silt fencing and hay bales around the equipment staging area  
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