5. Schedule of Work

a) DAY ELECTRIC shall not commence site work until MBARl has given DAY ELECTRIC notice to start the Work once all necessary permits are in hand.

b) The Shore Station Vertex fiberglass building is temporarily sited at the MBARl facility on Sandholdt Rd, Moss Landing and the interior of the building can be fitted out by the Contractor as soon as a contract is signed. The Vertex building will be moved to its final site shown on drawing Al as soon as the building foundations are complete by others. This is anticipated to be between mid Jan 2006 and mid May 2006. All of the work performed under this contract must be completed ready for Final Inspection within 6 weeks of the Vertex building being moved to its final destination.
