## Slide 1: WPDX Medium Power Easy Swap For MARS 2016 v3a
Thom Maughan
20 Mat 2016

## Slide 2: Block Diagram of What we want to build for MARS Toast goes in the Toaster
Input:
375v @ 2 amps
or
24v @ 30 amps
Load Light
Resonant Power
Load Control / Mon
802.11 PtP Radio
Ethernet Switch / Status Mon
Inrush Lim / 375 to 24v
150W continuous
240W peak

## Slide 3: First, Demonstrate 150 Watt Power and 100Mbps data transfer “Single slot toaster with a piece of toast” on ROV at 1000 meters
Input:
120vac @ 2.5 amps
100Mbps ethernet
Toaster Top View
“Toaster” Side View
Slot Components
“Toast” Side View
Components
Load Light
Resonant Power
Load Control / Mon
802.11 PtP Radio
Ethernet Switch / Status Mon
120v AC to 24v DC
150W Lights
1080p EthernetCamera

## Slide 4: Status 17 May 2016
Power transmit and receiver sub-assembly potted and tested for 150W continuous, 200W peak power
100 Mbps wifi radios tuned and potted antennas tested on: 1) bench in air, 2) double salinity saltwater, 3) test tank.
Load controller PCB designed, fabricated and firmware is written and tested.
Electrical loads and LED lights for connection status and load test at insert are designed, fabricated and tested. Two are built, ten more are in progress for ROV test
Electrical review by Paul McGill
In progress:
120vac to 24v DC 10 amp converter is designed thermally characterized and tested, not yet potted.
Wire harness for ROV connection is in progress planned for testing last week in May.
PoE IP Camera (substitute for PHOBOS) has been purchased and tested. Potting and pressure testing in progress.
Final assembly potting is planned for end of May after wire harness and converter sub-assembly.
ROV dive planned for June 15th