## Sheet1
Tasks to be Completed
| # | Conducted by | Hours | Days (9 hr) | Cost per Sample/Hr | Total
Ship/ROV
34 dives (16 days) | 16 | Kuhnz | 144 | 18
100 m Video Transects
12 Impact vs.Control stations, 3 each | 36 | Video lab (Kuhnz) | 36 | 4
10 Cable Stations, 2 each | 20 | Video lab (Kuhnz) | 20 | 2.2222
2 Skate Survey Stations, 3 each | 6 | Video lab (Kuhnz) | 6 | 0.66667
Infaunal Samples
Sieve/Preserve in formalin (top 5 cm fraction) | 60 | Benthic Bio Lab | 30 | 3.3333
Transfer to EtOH, transport, reporting for outside srvc | 60 | Kuhnz | 30 | 3.3333
12 Impact vs.Control stations, 5 each | 60 | ABA/MLML | na | na | 375 | 22500
Dubbing Dive Tapes for Agencies
Approximately 9 of the dives (covering just the route) | 9 | Video lab | 4.5 | 0.5
Grain Size
12 Impact vs.Control stations, 3 each | 36 | MLML/Ivano Aiello | na | na | 35 | 1260
CHN
12 Impact vs.Control stations, 3 each | 36 | Stanford (Dunbar Lab) |  |  | 30 | 1080
Data Analysis and Report Writing
Data and report preparation |  | Kuhnz | 80 | 8.8889
Finalize Report |  | Barry | 20 | 2.2222
Supplies
Collection | [5 empty] | 1500
Sample Processing | [5 empty] | 2000
Hazardous waste disposal (32 oz * 60 = 15 gallons) | [5 empty] | 200
Summary: | Hours | Days | Cost | 2019 | 2020
Kuhnz/Video Lab (Lab tech IV) | 320.5 | 37.6111 |  | 18 | 19.6
Benthic Bio Lab |  | 3.3333 |  | 1.3 | 2
Barry (Senior Scientist) | 40 | 2.2222 |  |  | 2.2 |  | 32
Outside Services |  |  | 24840 | 0 | 24840
Supplies |  |  | 3700 | 3700 | 0
Ship/Rov |  | 16 |  | 8 | 8