## Sheet1
[11 empty] | Data Analysis and Report Writing | Craig Dawe | 82.6408
Notes | [11 empty] | Duane Thompson | 60.37
Labor is 640hrs/yr Dawe D. Thompson, E Peltzer is estimated | [11 empty] | Rich Schramm | 75.4459
Expenses are estimated | [11 empty] | Michael Risi | 85.39
Income from port fees from last Lash PSR June 10 2020 | [11 empty] | Paul McGill | 85.3932
PSR Date July 8 2020 | [11 empty] | Peter Walz | 48.8
[12 empty] | Ray Thompson | 52.9417
[12 empty] | Doug Pargett | 75.9
Yr 5 Award | labor MARS Technician | Eng Support | labor MARS Manager | Science (Survey techs) | fringe 53% | income | indirect | expenses | ship time | Total |  | Jose Rosal | 55.99
and engineering support
01-02-2020 - 02-28-2021 | 23007.4 |  |  |  | 11856.25 |  | -14294.8 | -56702.41 | 235178.85 | 199045.29 |  | Ed Mellinger | 78.63
Jan | [10 empty] | Data Analysis and Report Writing | Linda Khunz | 44.13
Feb | [10 empty] | Data Analysis and Report Writing | Carson Ventana 2018 | 21800
Mar | [11 empty] | WF /DR | 31100
Apr
May
June
July | -2252.5254 |  | -3064.2217 |  | -2817.876 | 3000 | -7718.6578 | -7000
Aug | -3412.9173 |  | -4642.7601 |  | -4269.5091 | 3500 | -7560.8451 | -2500
Sep | -3412.9173 |  | -4642.7601 |  | -4269.5091 | 4000 | -7560.8451 | -2500
Oct | -3412.9173 |  | -4642.7601 |  | -4269.5091 | 4000 | -7560.8451 | -2500
Nov | -3412.9173 |  | -4642.7601 |  | -4269.5091 | 4000 | -7560.8451 | -2500
2020-12-01 | -3412.9173 |  | -4642.7601 |  | -4269.5091 | 4000 | -7560.8451 | -2500 | -21800
2021-01-01 | -3412.9173 |  | -4642.7601 | -7103.0064 | -8034.1024 | 4000 | -13103.321 | -2500
2021-02-01 | -3412.9173 |  | -4642.7601 |  | -4269.5091 | 4000 | -7560.8451 | -2500
sum of income -labor | -68809.4959 |  |  |  | -36469.0328 |  | -66187.0496 | -24500 | -21800 | -217765.5783
Project end of year projection | [5 empty] | 30500 |  |  |  | -18720.2883
Income from port fees As of June 10 2020 | [5 empty] | 150886.34
Balance for Node upgrade | [9 empty] | 162666.0517
Open Capital Projects | Budget |  | Paid | commited | remaining
MARS Node | 339600 |  | -45005.38 | -297257.13 | -2662.51
Note on B1: Craig Dawe: DRT,DF 2019
Note on D1: Craig Dawe: Dawe,Mcgilll,Schram,Schnitger
Note on E1: Craig Dawe: Linda Khunz Survey Hrs
Note on G1: Craig Dawe: port fees UW recovered Dec15, Soundscape, Diemos, RyanNPS,DSC deployed Dec15
Note on G3: Craig Dawe: expected income from UW APL, Ryan PAM, Haddock/Martini
Note on B12: Craig Dawe: DRT 640 hrs 2020
Note on D12: Craig Dawe: Dawe 640 hrs 2020
Note on G12: Craig Dawe: port fees Soundscape, Diemos, RyanNPS,DSC d
Note on G13: Craig Dawe: port fees Soundscape, Diemos, RyanNPS,DSC d
Note on G14: Craig Dawe: port fees Soundscape, Diemos, RyanNPS
Note on I14: Craig Dawe: Linda K Outside services contract
Note on E15: Craig Dawe: James Barry
Note on G15: Craig Dawe: port fees Soundscape, Diemos, RyanNPS
Note on G16: Craig Dawe: port fees Soundscape, Diemos, RyanNPS
Note on D17: Craig Dawe: Dawe + Peltzer, McGill, Mellinger 80, 40, 80
Note on D18: Craig Dawe: dawe 53 hr*.66
Note on G18: Craig Dawe: port fees Soundscape, Diemos, RyanNPS
Note on G19: Craig Dawe: port fees Soundscape, Diemos, RyanNPS, 50% SES
Note on G21: Craig Dawe: port fees Soundscape, Diemos, RyanNPS 50% SES, 50% Quest
Note on G22: Craig Dawe: port fees Soundscape, Diemos, RyanNPS, Quest
Note on G23: Craig Dawe: port fees Soundscape, Diemos, RyanNPS, Quest
Note on J23: Craig Dawe: Node Recovery
Note on E24: Craig Dawe: Ed Peltzer 80hrs
Note on G24: Craig Dawe: port fees Soundscape, Diemos, RyanNPS, Quest
Note on G25: Craig Dawe: port fees Soundscape, Diemos, RyanNPS, Quest
Note on K28: Craig Dawe: Projected Income total based on planned projects and current