Recovery and upgrade of the MARS node will be composed of several components:

- Identification and testing of replacement hardware/electronics

MVC requires recommissioning/testing

Alcatel Engineering has provided a quote for this work, $61k

Expected 3rd Qtr 2017 1 week Mellinger time for supervision/advise

Install new Engineering sensors

Test and verify engineering sensors 2-3 days Kecy

Integration to SSDS 1-2 weeks Schramm

Routers (surface and Subsea) specified and tested

New 1PPS circuit for node design/testing 1 week McGill

New fiber optic transport system for node/shore station testing.

- Build of “mini” node from identified/designed components

Small housing/end plate

ME design time 2nd /3rd Qtr 2017 4 weeks Casenave/Pargett

internals,

FEA

Thermal analysis

Fabrication 2 weeks

Accommodate FO, Data and Power connections (in house)

1PPS

Routers (subsea identified, Surface TBD)

600VDC-375/48vdc Port/node electronics (identified)

Control electronics (identified)

Gnd Flt cct (identified)

Oil filled Junction to accommodate 4 science ports

MARS node mock up frame and foam blocks

Modify to accommodate science ports

Modify to accommodate FO and Power ports

Use MARS deployment foam as buoyancy

Tank trials

Minimum 30 days in the tank

Data source connected to demonstrate through put

Camera and lights (TBD)

- Recovery

48 hrs prior to cruise shutdown MARS, short cable to gnd to discharge

12hr day on the RC plus mobilization day.

Ventana on standard benthic sled with swimmies and deep drawer

MacArtney Winch with 1200+m line and acoustic release

Mini node (100# negative with removable weights and homer beacon)

Lower node to sea floor and release close to MARS

Dive the ROV

Disconnect existing science projects and place connectors in parking positions.

MOBB

PAS

Martini Biolum Sensor

Etc

Disconnect FO and Power connections then place in parking positions

Remove the ballast weights from the MARS node and release to the surface.

Either store ballast weights in ROV drawer or place on seafloor for recovery later.

Retrieve “Mini” node

Place in TRF

Reconnect FO and power

Start mini node

Verify operation/connectivity

Run several complete Gnd Flt cycles

Reconnect all science projects

Test for connectivity/data

Run full gnd flt cycle after each connection.

Recover weights if required and return to surface

Recover ROV

Recover MARS node

- Refurbishment

Sample MVC/LV housing Fluorinert

Sample testing

Positive for HF/PFIB

Follow drain/cleaning/disposal procedure (TBD) per Chemists (Peltzer/Waltz 4th Qtr 2017 2 weeks)

Negative for HF/PFIB

Drain/filter/collect FC77 for re-use (procedure TBD)

Open Housings

MVC

Remove P1 MVC

Install Prod MVC

May require Alcatel supervision and testing or Mellinger.

(1 week 1st Qtr 2018)

Fill with fluorinert

Test and verify operation

Integration of MVC sensors into LV UI (1-2 weeks Schramm)

LV	Command and control will remain the same

UW APL LV control components

PC104 controller

Same User Interface currently in use

CLI back door

Remove:

Ciscos

Network electronics

EDFAs

OBC equipment

WHOI timing equipment

Install:

2-4 weeks ME time Casenave/Pargett

Mounting hardware

Thermal analysis verification

Lantech Routers (redundant)

New 1PPS

New OBC (serial port server with FO/Ether interface)

Full up system test dry 1 week McGill

Tank test

- Deployment

48 hrs prior to cruise shutdown MARS mini node, short cable to gnd to discharge

12hr day on the RC plus mobilization day.

Ventana on standard benthic sled with swimmies and deep drawer

MacArtney Winch with 1200+m line and acoustic release

MARS II node (100# negative with removable weights)

Lower node to sea floor and release close to MARS TRF

Dive the ROV

Disconnect existing science projects and place connectors in parking positions.

MOBB

PAS

Martini Biolum Sensor

Etc

Disconnect FO and Power connections then place in parking positions

Remove the ballast weights from the “Mini” node and release to the surface.

Either store ballast weights in ROV drawer or place on seafloor for recovery later.

Retrieve “MARS II” node

Place in TRF

Reconnect FO and power

Start mini node

Verify operation/connectivity

Run several complete Gnd Flt cycles

Reconnect all science projects

Test for connectivity/data

Run full gnd flt cycle after each connection.

Recover weights if required and return to surface

Recover ROV

Recover “Mini” node