1)Re- establish the Monterey Ocean Bottom Broadband (MOBB) on the MARS cabled observatory

Build a "Super" SIIM based on MARS Mini-node

Procure and lay new cable from MARS to MOBB

Refurbish MOBB electronics

Refurbish/replace Guralp Broadband seismometer

2) Install a Distributed Acoustic Sensing (DAS) unit on a fiber in the MARS cable

3) Install a DAS unit at the MOBB site connected to the Super SIIM

To achieve 1) above:

Build new housing for Super SIIM The Super SIIM will reuse some surplus hybrid fiber optic connectors and some new ODI 12way connector

Design                5 weeks

Manufacture       2.5 weeks

Assemble          3 weeks

Test                     3 weeks

Lay cable from MARS to MOBB           2 WF ship days (24hrs dive time)

Purchase cable (already specified) and quoted      (external)

Recover existing Guralp                       1RC 12hr ship day

Refurbish/replace seismometer        (external)

Redeploy seismometer

Refurbish Glass Bead Hopper    1 week

install/bed seismometer               1RC 12hr ship day

The program will be to install a fiber optic cable from an upgraded MARS node (new timing, new power scheme, new fiber optic port, new data distribution scheme) to the current MOBB site and then install an upgraded/expanded platform at the Trawl resistant frame.

1) excavate and recover the Guralp Broadband Seismometer (1 RC day)

redeploy the Guralp or equivalent and bed into the cassion (1 RC day)

2) build "super" SIIM

Ti housing and end penetrators

Housing internals			2.25 weeks machining

7 weeks design/assembly

3 weeks testing

2x Hybrid fiber ports  (MBARI Surplus need refurb) MARS connection

and future expansion possibly to include a subsea DAS in Phase 3

3x Wet mate 10/100 Ethernet, power (48v) 1PPS (quiet zone

implementation hydrophones current meters etc)

1x Dry mate connection to MOBB electronics (new)

IEEE 1588 capable switch for data/command/control distribution.

Slave clock

Slaved to IEEE 1588

1PPS output for legacy instrumentation

Local power switching and isolation (web based control, current design GFI/I board)

SSR/dry contact relay combination

Current sensing on all switched ports

Ground fault sensing on local power bus (48v)

3)Build MOBB Electronics housing

Glass spheres

1x 12way ODI panel mount connector to 12way bulkhead

Connection to Super SIIM

2x 8way ODI panel mount connector to 12way bulkhead

Connection to seismometer/current meter

EE time

ET time

ME/Shop time

4)Refurbish the Cable lay tool-sled

Larry Bird Time		4weeks

5)Deploy the Cable, Super SIIM, MOBB, Current meter

RV Western Flyer		2Days 24hrs dive time

RV Rachel Carson		3Days 12hr days