# Award 1514756 -
annual Project Report

### Cover

Federal Agency and Organization Element to Which Report is Submitted:

4900

Federal Grant or Other Identifying Number Assigned by Agency:

1514756

Project Title:

Funding to support Operations and Maintenance of the Monterey Accelerated Research System (MARS)

PD/PI Name:

- Craig Dawe, Principal Investigator

Recipient Organization:

Monterey Bay Aquarium Research Institute

Project/Grant Period:

03/15/2015 - 02/29/2020

Reporting Period:

03/01/2016 - 02/28/2017

Submitting Official (if other than PD/PI):

N/A

Submission Date:

N/A

Signature of Submitting Official (signature shall by submitted in accordance with agency specific instructions):

### Accomplishments - What was done? What was learned?

If there is nothing significant to report during this reporting period, please check "Nothing to Report" if applicable.

* Required fields

Top of Form

What are the major goals of the project?

- The goal of MARS Operations and Maintenance is to provide a facility that primarily hosts projects to develop technology for ocean science. Providing this facility for the scientific community makes it challenging to explain MARS O&M science impact. MARS O&M does not do science; we host scientists and technology developers in a very cost effective setting so that they can advance the frontiers of scientific understanding. In 2017 MARS hosted three projects, an acoustic study renewed from 2016 Sanctuary Soundscape (Formerly Passive Acoustic Sensing) Ryan MBARI/, an engineering test/long term data effort of a new Geodetic Seismic Sensor Module (GSSM) Wilcox/Manalang UW, and Serenity Light on MARS a project utilizing photon detectors to analyze bioluminescence in the ocean, Haddock/Martini MBARI.

- Efforts to upgrade the MARS electronics components continue to be a priority to the project team, Assembly of a “Mini-node” to ocean test the upgraded electronic components is nearing completion, the critical path is the High Voltage Underwater Mate-able connector from Teledyne - Ocean Design Inc (ODI). This component is under pending investigation for possible design flaws by ODI.

What was accomplished under these goals (you must provide information for at least one of the 4 categories below)?

Major Activities

- The major activities of the MARS observatory were to operate and maintain the cabled observatory in safe and efficient manner. As in previous years, MARS suffers from very few outages, most resulting from  power interruptions due to local utility failures, Internet Service Provider (ISP) outages and internal network hardware failures and configuration issues. The hardware failure caused a five-day outage of the system. This was identified as a power supply failure in one of the core routers in the system. These are schedule to be upgraded when the new node electronics upgrade is installed.  We also had a period of down time (4 days) for annual maintenance of the shore power system components.

- The Monterey Ocean Bottom Broadband Seismometer (MOBB) experienced a fault in one of its interconnects and failed. The system was partially recovered with plans to retrieve the remaining cable in 2018. They are currently preparing to apply for funding to re-install the cable plant and connect up the seismometer. Schedule has yet to be determined.

- Sanctuary Soundscape Research and Education Project (Ryan MBARI, Jeremy Goldbogen, Dave Cade Hopkins Marine Station, Independent researchers: Marjolaine Caillat, Mark Fischer, Alison Stimpert Moss Landing Marine Laboratories, John Joseph, Tetyana  Margolina Naval Postgraduate  School, Andrew DeVogelaere, Lisa Uttal NOAA/MBNMS, Simone Baumann‐Pickering, Anna Meyer Loebbecke, Jennifer Tricky Scripps, Brandon Southall UCSC) exchanged their equipment after a two year deployment and are expected to remain on the observatory for the foreseeable future.

- Serenity-Light on MARS (Haddock/Martini MBARI) deployed photon detectors and environmental instruments (CTD, O2, ADCP) to study bioluminescence at the MARS site. This project is funded by the Haddock lab and is expected to continue as long as the equipment does.

- Geodetic Seismic Sensor Module (GSSM) (Wilcox/Manalang UW) was deployed in June of 2017, they expect to remain on the observatory for an indefinite period, hoping to collaborate with other users with similar interests.

- The MARS team provides continuous support to users and prospective users. This is accomplished through consults on design issues particularly on the mechanical side but also with electrical/electronic and networking configurations. Testing services prior to deployments are supported, ensuring the highest possibility of success.

- Outreach to potential users is ongoing to inform about the capabilities of and the availability of MARS to the Science community and the public at large. Two new projects pending for MARS are a direct result of the outreach efforts. The first, a project from the Quest Institute (http://thequestinstitute.com/) who specialize in Science Technology Engineering and Math (STEM) education at the high school level are planning to deploy a student works space on MARS that will initially have a Remotely Operated Vehicle connected (student inspired project). Quest is currently scheduled for a April deployment, this may be delayed due to lead times on hardware. The second is a joint venture between MBARI and the Naval Postgraduate School, who plan to connect a 3D hydrophone to MARS augmenting the existing Sanctuary Soundscape data. They are scheduled for an October deployment.

- A third new project slated for 2018 is the “Deep Sea Connect” wireless power and data interface. This is a MBARI funded project directed at reducing the cost of connection to the observatory for both science and public education efforts. This project is leveraging off the previous MARS effort of the same type and to learn from the lessons of that project.

- MARS is also represented at the annual MBARI Open House conducting public outreach, informing the public about the capabilities and information coming from the deep ocean.

Specific Objectives:

- The primary objective of 2017 was to develop a set of components and systems that would address the issues highlighted in 2016, 48 volt power, subsea connector issues, aging routers, remote access to subsea devices and the timing system. Component upgrades for the subsea node have been purchased and tested on shore and are awaiting a High Voltage Nautilus connector before final assembly into a reduced capability replacement for the subsea LV electronics. Once the connector is in house the assembly will be completed and will be deployed pending a positive evaluation of the HV connector by the vendor.

Significant results:

- The MOBB failure last year was determined to be a failed seal on an o ring surface in one of the dry mate connectors. Because nothing was physically wrong with the connector it is suspected that the sealing surfaces were not clean which eventually (five years+) lead to the failure. The other significant finding of this failure was the need to develop a process to recover “extension” cables from the seafloor. Two attempts were undertaken with negative results each time. This is currently being discussed internally at MBARI.

- In June 2017 the Sanctuary Soundscape Research and Education (MBARI Internal Proj #901502 Dawe (MARS PI) as lead Engineer) was re-deployed/refreshed on the MARS observatory. This project is examining the soundscape of the Monterey Bay National Marine Sanctuary from a listening point near the MARS cabled observatory.  The Soundscape team submitted a new proposal that has been funded by MBARI/David and Lucile Packard Foundation to continue their work on a five year program

- Collaboration between the University of Washington Applied Physics Lab and MARS staff resulted in the successful testing and deployment (June) of the GSSM sensor package for long term engineering test and data collection.

- Severine Martini and the Haddock lab (MBARI) worked closely with MARS and MBARI staff to test and deploy (June) a pair of Photon detectors paired with re-tasked PhoBOS sensors (CTD,O2, ADCP) to study bioluminescence.

How have the results been disseminated to communities of interest?Bottom of Form

- MBARI maintains a public web site available to science and the public at large that allows access to much of the work conducted on MARS past and present. (http://www.mbari.org/at-sea/cabled-observatory/)

- Currently the Soundscape and Research Education project publishes the data online along with information about the project. (http://www.mbari.org/technology/solving-challenges/persistent-presence/mars-hydrophone/) The project also disseminates data and information through its collaborators NPS, Stanford/Hopkins, UCSD/Scripps, NOAA Exploration Center, MBNMS).  Recorded marine mammal vocalizations have been ported to a mobile playback system used in public outreach, local schools, Monterey Bay Aquarium. There have been four recent presentations on the Soundscape work this past January: Sanctuary Research Advisory Panel, Whalefest Monterey, Monterey Bay Aquarium, and an Environmental Lecture Series in Soquel. Publications are pending.

- GSSM has presented at AGU 2017 New Orleans, Ocean Sciences Meeting Portland Oregon and has been accepted for Oceans 2018 in Japan.

- Light on MARS participated in the MBARI Open house in 2017 educating the public about the project and its goals. They are preparing for two pending presentations in Spring 2018.

- External users of MARS are under no obligation to disseminate their data.

What do you plan to do during the next reporting period to accomplish the goals?

- Plans for 2017 slipped for three reasons, a delay from the connector vendor to supply the refurbished components, no evaluation of the suitability of the HV connector from the vendor and the shipyard for the RV Rachel Carson (Oct1-Jan 9) which pushed any deployment to 2018. The vendor still has not delivered the HV connector (Feb 2018). Recovery/Deployment dates are in the schedule.

- Assembly of the “Mini-node” will be completed once the HV connector is in house. Dependent on the results of the connector evaluation, the Mini-node will either be deployed (NSF/MBARI approval) and refurbishment of the primary node will begin or the Mini-node will wet tested and shelved until such time as dictated by need to replace the primary node.

- Two external consultations: Quest Institute, NPS/Geospectrum Technologies have been conducted to evaluate feasibility of a MARS deployment of projects and have resulted in two submissions for connection to the MARS Observatory currently schedule for April and October of 2018. The MARS team will provide consultation on device construction and connection interface and then testing on the Wet Node Simulator prior to deployment.

- Kang Ding of UMinn is still on the books to be deployed but his status is unknown. The MARS team has reached out to determine the status of this project to no avail. A date has been set aside for a deployment if requested.

Supporting Files

|  | Filename | Description | Uploaded By | Uploaded On |
| --- | --- | --- | --- | --- |
| (Remove) | MBNMS_PAM_2016_Oceans_V2.pdf | Soundscape Education Research Oceans 2016 presentation | Craig Dawe | 02/07/2017 |
| (Remove) | WPDX Medium Power Easy Swap For MARS 2016 v3a.pdf | Goals/Status (May 2016) of the Easy Swap connector effort | Craig Dawe | 02/07/2017 |
| (Remove) | WPDX_Medium_150W_100Mbps_BoardBullets.pdf | Outcome of trials of Easy Swap (June 2016) | Craig Dawe | 02/07/2017 |

Products

| Website | Hydrophone for passive acoustic monitoring. (+) | -- | -- | Complete | Edit details ¦ Delete |
| --- | --- | --- | --- | --- | --- |
| Website | MARS A new Way of Doing Oceanography. http://www.mbari.org/at-sea/cabled-...(+) | -- | -- | Complete | Edit details ¦ Delete |

|  | Complete | Edit details ¦ Delete |
| --- | --- | --- |

| Name | Most Senior Project Role | Nearest Person Month Worked | Status | Previous Participant | Actions |
| --- | --- | --- | --- | --- | --- |
| Dawe, Craig | PD/PI | 2 | Complete | -- | Edit details |
| Allen, Mandy | Other Professional | 1 | Complete | -- | Edit details ¦ Delete |
| Heller, Kenneth | Technician | 12 | Complete | Yes | Edit details ¦ Delete |

What other organizations have been involved as partners? Nothing to report

Your organizations from your last annual report have been added to this report. Please review each one for accuracy by clicking 'View details'.

|  Name | Type of Partner Organization | Location | Previous Organization | View Details | Actions |
| --- | --- | --- | --- | --- | --- |
| The David and Lucile Packard Foundation | Other Nonprofits | Palo Alto, California | Yes | View details | Edit details ¦ Delete |

What other collaborators or contacts have been involved?

List any other people or organizations involved in the project that were not separately reported as participants or partner organizations.

MBARI

- Bird, Larry EENG-Mechanical Eng-Mfg

- McGill, Paul RENG-Electrical Engineer

- Thompson, Ford RE Machinist

- Jose Rosal Technician

- Thomas Marion Technician

- Douglas Pargett Eng Mechanical Engineer

- Richard Schramm Eng Software Engineer

Teledyne Marine Systems

- Sean Brennan/Steven Gloor

What is the impact on the development of the principal discipline(s) of the project?

Describe how findings, results, techniques that were developed or extended, or other products from the project made an impact or are likely to make an impact on the base of knowledge, theory, and research and/or pedagogical methods in the principal disciplinary field(s) of the project.

- Lessons from the Easy-Swap connector effort have resulted in an MBARI funded project to continue the work to develop a reduced cost method of wireless data and power connectivity, MBARI project # 901802 Dawe (MARS PI) project manager.

- Serenity Light on MARS was deployed June 20th 2017, that same day the Sanctuary Soundscape developed issues with interference in their data collection. As a result of this the operational profile of the Serenity instruments was modified to allow for longer periods of less interference, satisfying the needs of both projects.

- MARS continues to provide a cost effective platform for testing of instruments destined for the OOI Cabled Array.  Versatile schedules, year round access to the node with transit/deployment/recovery capable of being completed in a single day provides increased confidence of a deployment on the larger array.

### Changes/ Problems

Changes in approach and reasons for change

- The pending evaluation of the Teledyne ODI High Voltage connector and the delivery delay of that connector and associated assemblies has had significant impact on the 2017 plans to recover and refurbish the MARS main electronics and power supply. It is hoped that evaluation and connector will be delivered early in 2018 and allow completion of the Mini-node. The evaluation of that same connector will determine the path forward for the refurbishment of the main node. Options include 1) Recover and refurbish (upgrade routers, timing, 48vdc, connector issues and aux communications) the main node with no changes to the power system, 2) as (1) above but replace the current power supply with a version better suited to the connector capabilities or 3) complete the Mini-node and wait till the main node fails or has too many issues to make it reliable then replace it with the completed Mini-node.

Actual or Anticipated problems or delays and actions or plans to resolve them

- The MARS team continues to work with the connector vendor to determine the cause of the failure of the HV connector, the outcome of this testing will determine the path to upgrade or prepare for an outage and replace the current electronics with the Mini-node.

Changes that have significant impact on expenditures

- If the path to Node refurbishment is to be completed with a new power scheme there will be some additional expenses to build a power supply however, they should fall within the current working budget of the project.

- If the Teledyne-ODI HV connector does not meet specifications and fails, this would necessitate a cableship repair.  The cableship repair to recover the entire node would be an expensive operation, but the system would be inoperable until such time as a repair was completed.