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Please provide the following information for the 2003 Annual Report to Nancy Barr by January 30, 2004.

Project Title: Core Video Annotation Data – MDUC (500055)


Project Leads: David Caress (Project Scientist)


Project Manager: Nancy Jacobsen Stout


Project Team: Jim Barry, Linda Kuhnz, Lonny Lundsten, Kim Reisenbichler, Kris Rodgers-Walz (resigned July 2003), Kyra Schlining, Susan von Thun


Collaborators (including affiliation):


· Project Summary

Purpose (same as previous years): The video annotation database derived from the ROVs Ventana and Tiburon is “core” data, which means that this database is considered important to the MBARI community as a whole. The collection, processing, and archiving of core data is provided on an institutional basis with oversight by the MBARI Data Users Committee (MDUC).

2003 Report: Annotation of ROV video was completed at either an “Outline” level (standard) or at a more comprehensive level if required by specific projects. Progress on video annotations advanced at a steady rate, with over 150 dive days, or 892 hours, annotated in “Outline” and “Detail” mode by year’s end. In 2003, a total of 221 ROV dives occurred, including 1147 hours (479 Ventana and 668 Tiburon) of new ROV video were generated. The annotations are now current within 2-3 months for all internal midwater, benthic, and geology dives.

Regular consultations were held among video staff to address annotation standards issues and scientists’ video annotation data requests were fulfilled as necessary. The video team also worked closely with IAG staff throughout the year to identify and resolve issues involving data collection and management protocol and standards. In 2003 the additional video archive vault in Building G was put to regular use and select archive tapes continued to be shipped offsite for safe storage. 
The use of the annotation database for scientific analyses continued to grow. In addition to populating and supporting use of this database for MBARI scientists, the video team members disseminated information about this unique database via multimedia and poster presentations at the 10th Deep Sea Biology Symposium and the 2003 Western Society of Naturalists meeting. Video Lab staff also participated in several cruises throughout the year and held numerous lab demonstrations for visiting colleagues.
· Graphics

Please include one figure or image to illustrate the project. Do not embed the image in your Word document, but rather provide it as a separate file. Graphs, charts, drawings, etc. are preferred as EPS files. Photos are best in high-resolution .tif, or as a print or slide. Since there will not be room for all submissions, you may provide a rough version of the graphic for consideration, with the understanding that a polished version will be required if your image is to be included in the report. 

· Captions

Include captions for any figures or images.

· Addenda 

Please refer to the 2002 annual report for samples of format and content for the following requested information:

· Mentorships

Evan Jones from the MAOS program completed an internship in the video lab and produced a web page (http://mww.mbari.org/itd/video/AnnotationRetrieval/Annotation_ids_liparids.htm) to assist video users in identifying liparids (snailfish).

· Invited Lectures

· Awards

· Degrees awarded

· Peer-reviewed publications

· Technical publications

