## BSY tasks
BSY SHIPYARD tasks
Rachel Carson (rev2 _Feb 7 , 2012)
item # | description | Duration | Status | Dates | Costs | Lead | other persons | Priority | Notes
| Deck tie downs defined |  | done |  | 0 | GregM ,Mark A
| Deck plug patterns defined |  | done |  | 0 | GregM ,Mark A
| SS tubing to wet lab |  | Moved to ML |  | 0 | ErichR,marka,reki
| CTD water inlet |  |  |  | 0 | ErichR,marka,reki |  |  | needs fixing, poor job at Bollinger
| Pads for van locks fab |  |  | 2012-02-14 | 0 | grch/comi
| Spot on deck for BSY |  |  |  | 0 | grch/comi
BSY Installation
| Modification of Freeing Ports |  |  |  | 0 | GregM ,Mark A
| BSY analysis |  | done |  | 0 | GregM ,Mark A
| Glosten analysis to send dwgs |  | YTBD |  | 0 | GregM ,Mark A
| ABS approval New Orleans |  | YTBD |  |  | GregM , Bay Design
| BSY quote AWP |  | YTBD
| Fire monitor pipe removal |  | done? |  |  | GregM
| AWP |  |  |  | 0 | GregM ,Mark A
| #1 Drain coolant and oil from engines |  | done |  | 2886 | GregM ,Mark A
| #3 rudders T & M |  | done |  | 4294
| #4 Sounding tubes |  |  |  | 17010 | GregM ,Mark A
| #5 Remove main deck hold downs |  | done |  | 9456 | GregM ,Mark A
| #6 Entry ramp |  |  |  | 8134 | GregM ,Mark A
| #7 Firemain pipe demo |  | done |  | 5760 | GregM ,Mark A
| #8 deck sockets |  |  |  | 17377 | GregM ,Mark A
| #10 Air Louvers |  |  |  | 1509 | GregM ,Mark A
| #11 Bow thruster access changes |  | done |  | 4923 | GregM ,Mark A
| #12 Roxtec transits |  |  |  | 8537 | GregM ,Mark A
| #13 Pipe brackets in ballast tank |  | done |  | 1400 | GregM ,Mark A
| #14 Transit holes in Ctl room & bow thruster frame |  |  |  | 0 | GregM ,Mark A
| Freeing Port mods |  | YTBD
| Sub panel install |  | YTBD
| Main deck condition ? |  | YTBD
| Surplus paint removal |  | YTBD
| Dock services Feb |  |  |  | 6120 |  |  |  | Current job has only 30 days at $6120
HYDRAULIC DESIGN
| Define design |  | ? |  |  | marka
| Define vendor for hydraulic work |  | done
| PO for hyd contractor |  | done |  |  | marka
| Installation of HPU's in ML |  | Moved to ML
| HPU purchase and cross deck Lobos |  | Moved to ML |  |  | marka
| Installation and HPU & piping |  |  |  | Original PO | marka,acbr
| ABS approved dwg |  |  |  | Original PO |  |  |  | T&M
| Hydraulic tank designed |  | done |  |  | marka-BSY |  |  | T&M
| Hydraulic tank fab |  |  |  |  | marka-BSY |  |  | T&M
| Hydraulic tank ABS approved |  | YTBD |  |  | ABS
BSY Installation
| Two 150kw generators |  |  |  | Original PO | marka
| purchase |  | done |  | Original PO | marka
| install |  | done |  | Original PO | marka-BSY
| wiring |  |  |  | Original PO | marka-BSY
| Panel modifications |  |  |  | Original PO | marka-BSY
| Load test |  |  |  | Original PO | marka-BSY
| Use existing switch panel to sail to ML |  |  |  |  | marka-BSY- Okuda
Submit design to BSY for evaluation
| Order new ER switch panel design |  | Moved to ML |  |  | marka-BSY
| Define design of new switch panel |  | done |  |  | Okuda/MarkA
| New switch panel out for bid |  | done
| Place order for new switch panel |  | YTBD
| Purchase new two sub panels for AC from Harris |  | done |  | 4000
| Install new sub panels in yard |  |  |  |  | marka-BSY
| Ordered ER Fans |  | done |  |  | GregM ,Mark A
| Install fans |  |  |  |  | GregM ,Mark A,BSY
Utility boxes on port ,mid-ships, strb
Strb Utility box
| Define I/o for Strb |  | done |  |  | Dawe/Marka /Okuda
| Add shore power to strb side |  | done |  |  | MarkA /Okuda |  |  | T&M
| Define location |  | done
| Design penetration method |  | done |  |  | Okuda/Bay Design/MarkA |  |  | T&M
| ABS dwg and approval |  |  |  |  | ABS
| Order parts |  |  |  |  | Okuda/MarkA
BSY to install
Port Utility box
| Define I/o for Port |  | done |  |  | Dawe/Marka /Okuda
| Add case drain |  | done
| Define location |  | done
| Design penetration method |  | done |  |  | Okuda/Bay Design/MarkA |  |  | T&M
| ABS dwg and approval |  |  |  |  | ABS
| Order parts |  |  |  |  | Okuda/MarkA
BSY to install
Mid-Ships Utility feed
| Define locations for starboard utility box |  | YTBD | [5 empty] | T&M
| Define I/O |  | done |  |  | Okuda/MarkA
Add case drain
Design penetration method
ABS dwg and approval
| Order parts |  |  |  |  | Okuda/MarkA
BSY to install
Inclining
| BSY to arrange weights |  |  |  | Original PO
| USCG to observe |  |  |  | Original PO
ABS to observe
Deck painting
Sewage on Starb side ?
| Deck Power aux equipment 480 3-phase? |  |  |  |  | dawe/marka

## Moss landing tasks
Moss Landing tasks
2012-02-07
item # | description | Duration | Status | Dates | Costs | Lead | other persons | Proirity | Notes
| ML outfitting | 267 days? |  |  | 594500
Engine room
| Modify existing switchgear | [6 empty] | 1
| Install new 480 sub panel | [6 empty] | 1
| Engine room tool boxes |  |  |  | 0 | marka |  | 2
Power systems
| Installation of hotel AC panels in forward section of the vessel |  |  |  | 0 | pilots |  | 1
| Design |  |  |  | 0 | Craigo |  | 1
| Purchase, panels, transformer, BOM |  |  |  | 0 |  |  | 1
| Install |  |  |  | 0 |  |  | 1
| Wiring |  |  |  | 0 |  |  | 1
| fabricate 45kva transformer Mount |  |  |  | 0 |  |  | 1
ROV Systems
| PDU |  |  |  | 0 | djo,mikeb,dacr |  | 1
| Order new cables if required |  |  |  | 0 | djo,mikeb,dacr |  | 1
| Specify mounts for LA shipyard ? |  |  |  | 0 | dacr |  | 1
| Xfer Pdu from Lobos to CRV |  |  |  | 0 | djo,mikeb,dacr |  | 1
| ROV RACKs |  |  |  | 0 | djo,mikeb,dacr,Schram |  | 1
| ROV AUX HPU |  |  |  | 0 | DMO,marka |  | 1 | in van
| Umblical transfer |  |  |  | 0 | djo,mikeb,dacr,efitz |  | 1
| Winch order |  | done |  | 0 | DMO,marka,MTECH |  | 1
| FAT test |  |  | 2012-04-15 | 0 | DJ |  | 1
| Winch delivery ? |  |  |  | 0 | dacr |  | 1
| DYNAIR |  |  |  | 0 | djo,mikeb,dacr;dfrench |  | 1
| USBL and Hydrophone |  |  |  | 0 |  |  | 1
| Mount head to pole |  |  |  | 0 | dacr,djo,mikeb; |  | 1
| Run cable from pole to Ctrl room |  |  |  | 0 | djo,mikeb,dacr |  | 1
| Interface I/O to operating computer |  |  |  | 0 | djo,mikeb,dacr |  | 1
| Offshore calibration and testing |  |  |  | 0 | djo,mikeb,dacr |  | 1
| Electrical wiring |  |  |  | 0 |  |  | 1
ROV CTL room
Inspect overhead piping
Rework piping
Bridge+ ships Electronics
Wire laddre pruchase
| Microwave rack |  |  |  | 0 | CraigO | Etch | 1
| SeaTel Antenna platform fab and install |  |  |  | 0 | Frank |  | 1
| Fabricate new foundation |  |  |  | 0 | CraigO | Etch | 1
| Install new foundation |  |  |  | 0 | CraigO | Etch | 1
| Cables for new foundation |  |  |  | 0 | Etch |  | 1
| Install SeaTel antenna |  |  |  | 0 | CraigO | Etch | 1
| Deck HD video camera |  |  |  | 0 | Etch |  | 1
| Install rear deck HD camera, run cable |  |  |  | 0 | Etech,MS |  | 1
| Automatic antenna pointer |  |  |  | 0 | CraigO | Etch | 1
| Install UHF antenna on mast, run antenna cable |  |  |  | 0 | CraigO | Etch | 1
| Install GPS antenna on mast, run antenna cable |  |  |  | 0 | CraigO | Etch | 1
| Gyro input to Seatel |  |  |  | 0 | CraigO | Etch | 1
| Moseley 6GHz |  |  |  | 0 | CraigO | Etch | 1
| Install DC supply |  |  |  | 0 | CraigO | Etch | 1
| Microwave ntework switch |  |  |  | 0 | CraigO | Etch | 1
| Quintum VOIP gateway |  |  |  | 0 | CraigO | Etch | 1
| HD switching |  |  |  | 0 | CraigO | Etch | 1
| Avenue HD rack |  |  |  | 0 | CraigO | Etch | 1
| NTT HVE9100 encoder |  |  |  | 0 | CraigO | Etch | 1
| AVN200 encoder |  |  |  | 0 | CraigO | Etch | 1
| Aminet 110 decoder |  |  |  | 0 | CraigO | Etch | 1
| Aninet 130 decoder |  |  |  | 0 | CraigO | Etch | 1
| Live Link audio panel |  |  |  | 0 | CraigO | Etch | 1
| Live Link audio panel remote |  |  |  | 0 | CraigO | Etch | 1
| Phone |  |  |  | 0 | Etch |  | 1
| Demobilize from Lobos |  |  |  | 0 | CraigO | Etch | 1
| KSU install |  |  |  | 0 | CraigO | Etch | 1
| cables runs to all locations |  |  |  | 0 | CraigO | Etch | 1
| install phones,terminate cables and mount |  |  |  | 0 | CraigO | Etch | 1
| Programming KSU Phone |  |  |  | 0 | CraigO | Etch | 1
| shore tie connection, install and cable |  |  |  | 0 | CraigO | Etch | 1
| Telluar Cell Phone |  |  |  | 0 |  |  | 1
| KUS tie in and program |  |  |  |  | CraigO |  | 1
| antennas and cables, mount& run cables |  |  |  | 0 | Etch | CraigO | 2
| below deck equipment,install transceivers |  |  |  | 0 | craigo |  | 1
| Wind sensor systems |  |  |  | 0 | Etch |  | 2
| Radar crossdeck |  |  |  | 0 | CraigO | Etch | 1
| Antenna plan |  |  |  | 0 | CraigO |  | 1
| Antenna mounts designed |  |  |  | 0 | CraigO |  | 1
| Antenna mounts installed |  |  |  | 0 | CraigO |  | 1
| UHF antenna for mooring support,Mount Antenna, run coax, terminate in drylab |  |  |  | 0 | craigo,Etech |  | 1
| 900 mhz antenna for AUV,Mount Antenna, run coax, terminate in drylab |  |  |  | 0 | craigo,Etech |  | 1
| Spare GPS antenna,Mount Antenna, run coax, terminate in drylab |  |  |  | 0 | craigo,Etech |  | 2
| RDF antenna,Mount Antenna, run coax, terminate in drylab |  |  |  | 0 | craigo,Etech |  | 1
| Telex VHF TX and RX antennas,Mount Antenna, run coax, terminate in drylab |  |  |  | 0 | craigo,Etech |  | 1
| GPS split to NTP,Mount Antenna, run coax, terminate in drylab |  |  |  | 0 | craigo,Etech |  | 1
| GPS Leica |  |  |  | 0 |  |  | 1
| locate and tie to dc supply |  |  |  | 0 | craigo,Etech |  | 1
| progarm serial ports |  |  |  | 0 | craigo,Etech |  | 1
| Sperry FOG |  |  |  | 0 |  |  | 1
| mount sensor |  |  |  | 0 | dacr;djo;dfrench,MS |  | 1
| mount display |  |  |  | 0 | dacr;djo;dfrench |  | 1
| run control cable |  |  |  | 0 | dacr;djo;dfrench |  | 1
| tie to autopilot |  |  |  | 0 | dacr;djo;dfrench |  | 1
| tie to radar |  |  |  | 0 | dacr;djo;dfrench |  | 1
| locate and tie to dc supply |  |  |  | 0 | dacr;djo;dfrench |  | 1
| TSS VRU |  |  |  | 0 | dacr,mikeb,djo |  | 1
| VSAT |  |  |  | 0 | dfrench,marka |  | 2
| Vsat mounting |  |  |  | 0 | dfrench,marka |  | 2
| Vsat wiring |  |  |  | 0 | dfrench,marka |  | 2
| Vsat contract |  |  |  | 0 | aaron |  | 2
Dry lab systems
| Install new slides and machines in the rack |  |  |  | 0 | Schram,gomes,Etech |  | 1
| Install new display (Vorne included) |  |  |  | 0 | Schram,gomes,Etech |  | 1
| Build new combined navproc/logger server to replace old, configure O.S., serial ports, spi bus,software, build, test |  |  |  | 0 | Schram |  | 1
| Dataprobe work: delayed fixes, IP changes, help files (these are tied to cabling and server documentation changes) |  |  |  | 0 | Schram |  | 1
| ArcNav changes |  |  |  | 0 | McCann |  | 1
| VARS Changes |  |  |  | 0 | Brian S |  | 1
| Rebuild custom cables |  |  |  | 0 | Schram |  | 1
| Build ethernet cables to length |  |  |  | 0 | Schram |  | 1
| Add wind sensor back into data flow |  |  |  | 0 | Schram |  | 1
| KVM installation and configuration |  |  |  | 0 | Schram |  | 1
| FOG conversion |  |  |  | 0 | Schram |  | 1
| After powering all systems up, ring out everything test and troubleshoot |  |  |  | 0 | Schram |  | 1
| tables |  |  |  | 0 | dacr,reki |  | 1
| chairs |  |  |  | 0 | dacr,reki |  | 1
| Monitors/video wall |  |  |  | 0 | dacr,reki |  | 1
| newtwork drops |  |  |  | 0 | IS,Pete B |  | 1
| wireless network |  |  |  | 0 | IS,Pete B |  | 1
| network |  |  |  | 0 | IS,Pete B |  | 1
| phone |  |  |  | 0 | Support Eng,craigo |  | 1
| Utility GPS feed |  |  |  | 0 | craigo,MTECH,Etech,dfrench |  | 1
| CTD deck box connection |  |  |  | 0 | ErichR |  | 1
| Utility GPS feed |  |  |  | 0 | craigo,MTECH,Etech,dfrench |  | 1
| Telex intercom base and distribution |  |  |  | 0 | dfrench.Etech |  | 1
| CCTV |  |  |  | 0 | dfrench,Support Eng,marka,aaron |  | 1
| Evaluate CRV layout for CCTV cameras. Ethernet or Coax? |  |  |  | 0 | dfrench
| Consult with ships personnel about placement |  |  |  | 0 | dfrench
NETWORK + data systems
| NTP antenna |  |  |  | 0 | IS,Pete B |  | 1
| NTP time server |  |  |  | 0 | IS,Pete B |  | 1
| SOCKEYE |  |  |  | 0 | IS,Pete B |  | 1
| CISCO router |  |  |  | 0 | IS,Pete B |  | 1
| DATABASE server Glacier wind |  |  |  | 0 | IS,Pete B,schiling |  | 1
| UNIX remove? |  |  |  | 0 | IS,Pete B |  | 1
| CORONA |  |  |  | 0 | IS,Pete B |  | 1
| Network Switches |  |  |  | 0 | IS,Pete B |  | 1
| WiFi Wireless network base stations |  |  |  | 0 | IS,Pete B |  | 2
| VARS server |  |  |  | 0 | IS,Pete B,schiling |  | 1
| YODEL Sonar computer |  |  |  | 0 | djo,dacr |  | 1
| UCTD/PCTD |  |  |  | 0 | ErichR,Schram |  | 1
| PCNAVPROC |  |  |  | 0 | Support Eng,Schram |  | 1
| INFERNALES |  |  |  | 0 | Schram,Support Eng;djo |  | 1
| PCLOGGER |  |  |  | 0 | Schram,Support Eng |  | 1
| GRAN ROJO (SCI WORKSTATION) |  |  |  | 0 | IS,Pete B |  | 1
| HAWKEYE |  |  |  | 0 | SteveR,djo,IS,PeteB |  | 1
| TYTO ALBA |  |  |  | 0 | djo,dacr |  | 1
| Winfrog |  |  |  | 0 | djo,mikeb,Schram |  | 1
| Bridge Nav |  |  |  | 0 | Pete B,IS,djo |  | 1
| AftNav |  |  |  | 0 | Pete B,IS,djo |  | 1
Aft deck
| CTD winch connections |  |  |  | 0 |  |  | 1
| desgin mount |  |  |  | 0 | craigo |  | 1
| Electrical wiring |  |  |  | 0 |  |  | 1
| Hydrualics hoses |  |  |  | 0 | Aiello |  | 1
| Flagsheave location |  |  |  | 0 |  |  | 1
| new flagsheve mount |  |  |  | 0 |  |  | 1
| spec and buy new capstan | [6 empty] | 1
| Capstan install |  |  |  | 0 |  |  | 1
| desgin capstan base |  |  |  | 0 | craigo |  | 1
| Small boat mount |  |  |  |  | maudlin |  | 3
| Purchase new Small boat |  |  |  | 40000
| 16ft purchase |  |  |  | 40000
| cradle fab |  |  |  | 0 | grch | maudlin | 2
| Convert AK25 |  |  |  |  | Dawe | Thomas | 1
| Install AK25 |  |  |  |  | Dawe | Thomas | 1
| Van cam locks install |  |  |  |  | maudlin |  | 1
| PM43 | [6 empty] | 1
| PM43 demob |  |  |  |  | Aiello |  | 1
| PM43 mounts |  |  |  |  | Aiello |  | 1
| PM43 hydraulic hoses |  |  |  |  | Aiello |  | 1
| PM43 wiring to TMS |  |  |  |  | Aiello
| Telex, camera |  |  |  |  | French
| hpu remote… |  |  |  |  | Aiello
Science van
| power |  |  |  | 0 | marka |  | 1
| water |  |  |  | 0 | marka |  | 1
| drain |  |  |  | 0 | marka |  | 1
| GPS feed |  |  |  | 0 | Etech | craigo
| Underway CTD system is moved with van |  |  |  | 0 | ErichR |  | 1
| Sea Water Water inlet |  |  |  | 0 | ErichR |  | 1
| communications |  |  |  | 0 |  |  | 1
| phone |  |  |  | 0 | Etech | craigo | 1
| Network |  |  |  | 0 | IS |  | 1
| Telex |  |  |  | 0 | dfrench |  | 3
| ROV-AUV van workshop bulit |  |  |  |  | dacr |  | 1
| air |  |  |  | 0 | dacr | Thomas | 1
| power |  |  |  | 0 | dacr | Thomas | 1
| communications |  |  |  | 0 | dacr | Thomas | 1
| phone |  |  |  | 0 | Etech | craigo | 1
| network |  |  |  | 0 | IS |  | 1
| intercom telex |  |  |  | 0 | dfrench |  | 2
| Equipment racks AUV |  |  |  | 0 |  |  | 1
Dock improvements
| Shore Power Cord extention |  |  |  | 0 | contractor |  | 1
| EMK dock improvements |  |  |  | 0 |  |  | 1
| Gangway |  |  |  | 4500 | grch,acbr |  | 1
| Shore phone and network connection extention |  |  |  |  | Etech | craigo | 1
wish list
| Network drops staterooms ? |  |  |  | 0 | PeterB,IS
| Flatscreens staterooms ? |  |  |  | 0
??? Stuff
| J Frame |  |  |  | 0 |  |  |  | descope
| Mini Hiab 90 ? |  |  |  | 0
| Hydraphone head and cable |  |  |  | 0
| Fridge |  |  |  | 0
| Sat TV |  |  |  | 0
| Lista Cabinets |  |  |  | 0