## General tasks
General Tasks
Week | Task Description | Assigment | Plan ready? | BOM in hand? | Notes

## control room
Control Room tasks
Week | Task Description | Assigment | Plan ready? | BOM in hand? | Notes
1 | Fix pipes
1 | Install Air cond ducts
1 | Build overhead wireway to tray transitions
1 | Template console
1 | paint and trip (overhead)
2 | Celing reinstall
2 | Install wire trays on walls |  |  |  | Pilots to buy
2 | install 208 panels |  |  | Yes
2 | Wire 120v circuits |  |  | Yes
2 | Install racks

## Dry Lab
Dry tasks
Week | Task Description | Assigment | Plan ready? | BOM in hand? | Notes
1 | Scope out job
1 | remove wall panels
2 | Wire 120v circuits
2 | Install wire trays on walls
2 | Install racks

## fwd machinery
Foreward machinery space tasks
Week | Task Description | Assigment | Plan ready? | BOM in hand? | Notes
1 | Hotel Transformer |  | Yes | Yes
1 | Hotel Panel |  | Yes | Yes
1 | 480 runs to ER
1 | 208 runs to control room
1 | Scope out Sewater system
2 | Wire Hotel panel |  |  | Yes
2 | Wire panel loads
2 | Wire runs to ER
2 | Wire feed runs to Seawater pump
3 | Install Seawater pump system
3 | Install PDU and transformer mounts

## Engine room
Engine Room Tasks
Week | Task Description | Assigment | Plan ready? | BOM in hand? | Notes
1 | Shore Tie temp
1 | 480 sub panel
1 | layout hydraulics
1 | layout ROV sub-panel
2 | Sub Feeds
2 | HPU Feed
2 | Shore Tie
2 | TMS Feed
3 | Hydraulic System
3 | Mount Pump Panel
3 | Plumb
4 | Starboard Utility Box connections
4 | AK25 connections
4 | PM43 connections

## Deck
Deck tasks
Week | Task Description | Assigment | Plan ready? | BOM in hand? | Notes
1 | Check Van camlocks
1 | Mount Vans (check the cam locks)
1

## Pilot house
Pilot House tasks
Week | Task Description | Assigment | Plan ready? | BOM in hand? | Notes
1 | n/a
2 | n/a
3 | n/a
4 | Antenna instalation