Converting MBARI’s Video Tapes to Digital Files:

A multi-year preservation endeavor

DRAFT 12/19/20

BACKGROUND

The thirty-year library of deep sea imagery at MBARI constitutes an actively curated library of indexed images that has grown to over 26,000 hours of recordings with over six million annotations. Together with the associated environmental data, this archival record and observational database forms a one-of-a-kind resource for the scientific community. It describes the biological, chemical, geological, and physical aspects of the Monterey Bay submarine canyon and other deep-sea areas including the Pacific Northwest, Northern California, Hawaii, the Gulf of California, Taiwan, and the Canadian arctic. This knowledgebase of information is available to researchers around the world through access to the MBARI Deep Sea Guide and the free distribution of VARS data and software.

This rich historical record is a critical research asset. Projects that use the video archive and associated contextual knowledge often use data extracted from across the entire library. Thus, the preservation and curation of this important and unique library — all of the visual records of deep-sea observations collected at MBARI since ROV dives began in 1988 — requires that all of the proprietary tapes be transcoded into modern file-based records. Given the number of individual tapes and the precision required to preserve the timecode links to the VARS database, the tape conversion process is an enormous endeavor.

PROJECT OBJECTIVE

The video tape transcoding project will convert existing MBARI video tapes to digital files and integrate them into the new MBARI Media Management (M3) system and VARS annotation and Query systems. This video archive includes Sony Digital Betacam and Panasonic D5 high-definition formats. A large number of these tapes, primarily HD tapes, are single copies with no back up copy. These are the first priority for transcoding. In addition, the physical assets are aging and the Panasonic and Sony tape equipment are becoming harder to maintain. Therefore, it will be important to finish digitizing assets in the next two years to ensure we capture all the information before tape degradation and equipment obsolescence. In order for the majority of the video assets to remain available to staff, we envision this process will be completed in phases as tape archives are transferred to vendor and subsequently stored offsite until they are released for recycling.

RESEARCH AND EVALUATION

Vendor research

- Created abbreviated and detailed synopses of requirements to discuss with vendors (e.g. tape number and format, codec, file naming, metadata, schedule, QC, delivery methods, etc.) (ADDENDA A & B)

- Defined criteria to be evaluated and compared vendors in terms of communication/relationships, location, cost per tape or batch, cost of equipment + staff, delivery method, availability/timeline, turnaround time, equipment availability (e.g. DigiBeta or HD decks), etc.

- Current vendor bids:

| Vendor | Contact | Location | Quote Price |
| --- | --- | --- | --- |
| Advanced Media LLC | Nimrod Zalmanowitz | Los Angeles, CA | $1,732,672 |
| Blackbox Media Mgmt Services (approx. bid) | Jeff Beaulieu | London, England, UK | $1,053,500 |
| Iron Mountain Entertainment Services | Allan Schollnick | Hollywood, CA | $932,000 |
| Preserve South, Inc | Emily Halevy | Buford, GA | $761,021 |
| Visual Data Media Services | Juliet Carriker​ | Burbank, CA | $1,345,614 |

Considerations for transcoding onsite

- Early in our investigations we reviewed the SAMMA robotic system (Oracle’s Front Porch Digital). The systems were the gold standard for the Library of Congress, the Smithsonian, and other institutions involved with preserving video. The cost quotes we received exceeded $700,000 for the initial equipment set up alone. Additional costs would have included annual maintenance, training, physical space, and staffing (e.g. as in 2. Below).

- At this point in time, there are numerous out-of-box systems that are more customizable and cost-effective, including Telestream, CineDeck, and our own M3RS (Softron; shipboard capture system). All of the vendors that we have engaged with, who have the capacity and technical skill to handle our volumes and high-resolution content, use these systems as opposed to the SAMMA systems. The cost of completing the tape transcoding in house, in an equivalent manner to the Iron Mountain bid, is ESTIMATED to exceed $802,000 (ADDENDUM D).

CONCLUSION

From our careful estimation, the best path forward is to pursue a contract with Iron Mountain Entertainment Services in Hollywood, California. The other vendors were too expensive (up to $1.7M), too far away (e.g. UK, Georgia), unable to meet our specifications, or a combination of these factors. Additionally, we have an established rapport and business relationship with Iron Mountain Entertainment Services (IMES) as they have provided many bids for us in the past and have been storing our tape duplicates for decades.

We do not think it would be wise or reasonable to attempt this digitization project at MBARI. The risks, potential dollar costs, and staff time are simply too high for a one-time project (again, see factors outlined in ADDENDUM D). Attempting to do this inhouse, even with the hiring of two new full-time video technicians, would require a great deal of time for set up and oversight and after completion, the equipment is not be needed for future projects. This would not be a wise use of time for our highly-skilled research technicians, whom we have invested resources into making expert annotators, data, and process specialists. Thus, we also believe our overall productivity and morale would be negatively affected.

PROJECT TIMELINE

- 2015-2018 Preliminary efforts to plan for conversion of video tapes including detailed workflow, specifications, and many vendor bids. Most significant limiting or unknown factors were: staff availability, budget, fluctuating status of VARS, video tape longevity, implementation of new file recording systems, lack of onsite storage, and uncertainty about building G.

- 2019 Q1 and Q2

  - VideoTAG works to formulate an overall strategic vision for the capture, management, use, storage and distribution of massive quantities of video files (converted and new) results in new, long-term storage solutions that will finally make storage of all of these video files a reality. With that hurdle overcome, we also recommended conversion of all video tapes to preserve this invaluable scientific record, enable continuation of research projects that extract data from across the entire library, and to further machine learning developments and future data mining efforts.

  - Adoption of the video file capture and management system (M3RS) and associated upgrades to VARS near completion and allow us to solidify our file formats and related requirements needed to put out final specifications to vendors.

- 2019 Q3 and Q4

  - June to August. RFP w/ specifications went out to our top five industry-level vendors (several consumer level vendors unable to come close to our specs were also eliminated at that point). Worked with top three vendors — determined Iron Mountain best suited to meet our needs.

  - September to November. Initiated and completed initial Proof of Concept by Iron Mountain. Continued negotiating contract. MBARI agreed to loan HD decks (reduces our cost); Iron Mountain agreed to adopt our preferred file generation hardware and workflow to meet our precise specifications with contractual commitment (ADDENDUM E).

  - December. Final proposal received from Iron Mountain Entertainment Services (IMES) (ADDENDUM F)

- 2020

  - Finalize contract with IMES. They require MBARI to commit to 1/3 of tapes before proceeding with Softron system purchase at their facility. Need to revise quote to include tape storage and outline the loan agreement of MBARI HD decks (IMES to maintain decks and return to MBARI in good working condition). DCR (digital storage option) can be removed.

  - Resolve LTO firmware upgrade on MBARI-side that is preventing reading of LTO-8 tapes (Neil)

  - Initiate contract and begin work.

- 2020–2022

  - Project continuation and completion

ADDENDUM A

Specification for vendors

Initial specifications for vendors:

- Vendor to support tape formats — Sony Beta SP, Sony Digital Betacam (DigiBeta), Panasonic D5 High Definition (HD).

- Vendor to support video compression codecs — ProResHQ (Apple) is MBARI archival format and H.264 is proxy video

- Provide QC (Quality control) and checksum reports (file verification process) report for each tape asset/file

- Deliver progress, verification reports, and asset images for the project on a weekly or bi-weekly schedule

- Follow custom file naming protocol with vehicle, dive, tape number HD or SD, sequence (to denote video segment order from tape), and timecode of first frame for each video, if possible. Example, D451_1HD_3_01103026.mov (e.g. auto-naming, manual entries, metadata extracted from userbits, encoded in atom headers).

- Video tapes will be digitized to two video file clips for 32-min tapes or to four clips for 64-min tapes, and tracked with sequence number in filename.

- Retain original HD or DigiBeta timecode in ProRes file

- Digitize audio track onto both archival and proxy video files

- Media to be delivered on provided hardware, options are LTO tape as primary; cloud download or hard drives (portable or larger) as alternate; or a combination of these. In addition, media stored at vendor facility for 6 months to one year as back-up, cloud storage options may be required

- Location of digitization, either on-site or at vendor facility or some combination of both

- Need short and long-term storage options for video tape assets after digitization. Store assets offsite until final confirmation of video content then release for recycling after 1–2 years

- Completion of project in 18 to 24 months

ADDENDUM B (1 and 2)

Detailed workflow and tasks for vendors and MBARI

(1 overview and 2 detailed workflow)

ADDENDUM C

Detailed preparation and management tasks for MBARI

MBARI Staff Tasks:

Gather precise inventory of originals and back-ups in three current facilities:

1.    MBARI Building A: all originals, D5 HD and DigiBeta

2.    MBARI Building G: originals and dubs, D5 HD and DigiBeta (in addition, some BetacamSP originals are stored in boxes in this vault)

3.    Iron Mountain (Hollywood, CA): 10,000+ DigiBeta dubs and Betacam SP originals

Tape Handling from MBARI vaults:

1.   Additional labeling/barcoding of tapes (?), e.g. to indicate destination, recycling fate, or possibly additional metadata required for conversion to file processes for vendors (e.g. for proper file naming)

3.    Boxing & labeling/barcoding of boxes

4.    Shipment or delivery method(s), vendor pickup with climate-controlled trucks?

5.    Records of tape assets sent and received, including all metadata, barcode, label information/legend.

Tasks during vendor digitization:

- Follow progress of work through vendor project database and vendor QC reports on a weekly or bi-weekly schedule

- Check asset images and filename conventions, monitor QC and checksums

- Receive digitized media at MBARI, load LTO tapes in our LTFS or connect portable hard drives for transfer to staging area on M3.

- File format — i.e., converted video files from tapes should be compatible with those generated by the new M3 video digitization processes. E.g. dubs will need to have record time (not local computer time, which is what 1Beyond will grab), begin processing files for filename renaming, spot check video and audio content, and ensure timecode included on ProRes files.

- File registration – into VARS/M3 (MAM/method TBD)

- Automate the transfer of registered ProRes files to LTO tape archive after filename corrections are completed, H264 files to stay on M3 unless too numerous then put older ones on LTO tape (1988 to approx. 1999 is SD video, will be accessed less).

ADDENDUM D

Cost of transcoding tapes at MBARI

$802,000+

A comparison using the same criteria as our preferred vendor, Iron Mountain.

Expenses $702,000

- Eight recording stations $199,000

  - $34,000 Eight recording stations - 4 Digital Betacam and 4 HD. Costs estimates include purchases (2 @ $10K) and maintenance ($12K per year)

  - $80,000 8 video ingest stations, e.g., M3RS setups (Mac-based Softron) @ $10k each. Similar ingest setup using Cinedeck (Windows-based; used at MBA) is twice as much @ $177,000.

  - $60,000 RAIDs (4 @ $5k) and LTO tape equipment & media (2 @ $20k) for storage/transport of files to MBARI

  - $25,000 Software and barcoding systems to manage physical tapes and metadata. Includes equipment for imaging each asset to retain original label data.

  - $??? Tape monitoring and cleaning – standard infrastructure in vendor facilities, but costs unknown for MBARI.

  - $??? QC processing (e.g Automatic checksums, levels, drop/black frames, etc. by Tektronix Aurora; plus, 3 point QC audible/visual checks by trained technician) and implementation for every file (specialized MBARI or off-the-shelf software)

- Two FT technicians $316,000

  - 2080 hours minus 20% leave, overhead = 1664 hours available to work annually. 26,000 hours of tape to process/2 people = 13,000 hours each/4 tapes at once = 3250/1664 hours available = 2 years to complete job.

  - $316,000 Pay rate of $25/hour minimum (can go to $40+) for skilled video technician + 52% ($13) overhead = 38 x 4160 = 158,080 x 2 years = $316,160

- Space and transportation $187,000

  - $72,000 minimum estimate. MBARI does not currently have a suitable space to set up equipment, stage tapes, and house two additional employees. Estimate for commercial space 1200 square feet, $2.00/sq. foot space (e.g. Marina) = $2400 + utilities, insurance, etc. = approximately $3000 / month. Additional expenses may include furnishings, supplies, parking, etc.

  - $25,000 Transportation of tapes and finished files to/from MBARI. Small van plus insurance and registration.

  - $90,000 Building G is going away (?) so another suitable temporary storage site would be needed for several years (est. $30k/yr) until successful transfers from original video tapes are verified. Many preservation specialists recommend never destroying originals.

Intangibles and unknowns $125,000 (guess - likely a PT Video Lab staff each year)

- Spin up time on equipment and recording workflow for existing and new staff.

- Time for setting up and managing space, hiring and managing technicians.

- High risks as this is not our area of expertise. The responsibility, infrastructure, and guarantee that a vendor would provide is invaluable.

- Reduces productivity of existing staff, especially considering we’ve recently become suitably staffed for our current workload.

ADDENDUM E

Letter of intent to negotiate contract w/ Iron Mountain

ADDENDUM F

Iron Mountain Proposal (Final?) 12/16/19

Separate attachment