## Video Strategy Overall Scope
DRAFT A new strategic vision and comprehensive plan for the future of imagery at MBARI
| VIDEO TAG |  | CORE ANNOTATION | MACHINE LEARNING for IMAGERY | ROV Camera Upgrades
| 901603 |  | 500055 | potentially a new, separate project in the future | 901900
Core functions | Lead strategic vision/plan for a sustainable institutional video program at MBARI: Video acquisition Video curation Video life cycle/data policy Video analysis Image Machine learning | >>> | Video recording (M3RS) Video curation (management + storage) (M3) VARS software Annotation policy, methods, implementation Ancillary functions (DSG, Embargos, QC/QA) | Machine learning tool development for internal imagery analysisys work/ problems | ROV camera selection ROV integration > acquisition
Core Team | Duane Edgington Danelle Cline Nancy Jacobsen Stout Lonny Lundsten Todd Ruston Mark Chaffey Management Team (Doug Au, Jim Barry, others as needed) |  | Nancy Jacobsen Stout Brian Schlining (VARS SE) Lonny Lundsten Todd Ruston (Storage) | Danelle Cline Duane Edgington Brian Schlining Nancy Jacobsen Stout Lonny Lundsten Research representation | Mark Chaffey (design) Lonny Lundsten (M3RS integration) Dave French (ROV integration) Steve Haddock (Sci. impact)
Stakeholders (additional or future team membrs, labs, projects) | All of MBARI |  | Kyra Schlining Susan von Thun Linda Kuhnz Megan Basset | Ben Yair Raanan John Ryan Steve Rock Lab Bioinspiration Lab Acoustics Lab | Bryan Schaeffer (Ricketts) DJ Osborne (Ventana) Dale Graves (MiniROV) Todd Walsh (maint, calib)
Progress to date | Adisory on video and machine learning projects Investigation of current machine learning technologies Collaborations with external peers on projects specific to deep-sea domain |  | 30-year's of video assets, annotations, and publications VARS and DSG M3 and M3RS (modern file-based system | Deep-learning methods successfully applied to still images Significant experience developing effective training datasets (stills and video) Shifted focus to machine learning technologies for video | COTS camera testing (75%) ROV integration readiness Doc Ricketts (%) Ventana (%) MiniROV (%)
Future high-level goals | Develop and maintain overall strategic vision |  | VARS software modifications/maintenace Core annotation/backlog (humans + AI) | Integrated machine learing into everyday annotation workflow MBARI Model Zoo (published models and procedures) MBARI VideoNet (currated, hierarchical) | Specify camera upgrades that improve resolution for science Ensure camera technology does not become obsolete
Challenges and identified solutions | Lack of institute strategy and priority for video and machine learning projects Increasing data streams and resource time to manage them |  | Diversify the pool of software engineers for developing tools to aid processing and analysis | Secure funds for: Engaging active external collaboration Cloud-based, serverless ML evaluations/solutions internal computational capabilities | Incompatabilities among platforms Wide array of COTS cameras to evaluate, many low resolution
Related projects | TBD |  | TBD | TBD | TBD
Project web pages (to be created or updated) | New internal web page to eventually include: Project summary Strategic vision Final version of this matrix |  | mww.mbari.org/itd/video/annotation_data_retrieval.html | www.mbari.org/technology/emerging-current-tools/machine-learning/ | New internal page to eventaully include: Project summary Link to proposal, desgin review Camera testing resulsts (.xls) ROV diagrams, specs, etc

## TEAM NOTES
| VIDEO TAG | CORE ANNOTATION | MACHINE LEARNING for IMAGERY | ROV Camera Upgrades
| 901603 | 500055 | potentially a new, separate project in the future | 901900
TEAM NOTES
NOTES = To Do for developing each project | *rework project & address MT feedback *project brown bag? Not before Phase II as MT suggests *clarity & mtg w/ MT *finish matrix *new web page | *proposal budget + resource adjustments. (The team places higher priority on VARS KB updates than some of the Milestone 3 items) *Clarify hours vs time to annotate *annotation progress reports by PI (75% done) *PI discussions re: priorities (anno, digit, ML) *web page updates | *make a new project *new web page | *re-write portions of project, change name *new web page