## Sheet1
| Gene | Users | Jon or Brett or Gene | Jim S. | $$$ Costs
Pick a preferred design | 0.5 | 0.5 | 0.5
Final FEA work |  |  | 7
Optimize W/D ratio and weight in water
Fix local high stress areas
Make sure connector bores don’t distort unacceptably for proper sealing
Re-do FEA with outer O-ring failure
Equalize bearing pressure at dual O-ring grooves
Check calcs |  |  | 1
Generate model drawings & check |  |  | 2
Work with Oremet Wah-Chang (and Jon) to optimize manufacturability |  |  | 1
Generate as cast drawings & check |  |  | 1
Generate "as Machined" drawings |  |  | 2
Buy 1, 10, 100(?)
Patterns |  |  |  |  | 5000
Casting |  |  |  |  | 6500
Machining |  |  |  |  | 12000 | This is a bit of a guess but the last set of halves cost $7400 each @ Tapemation, these should require somewhat less machining
Pressure test at Pt. Hueneme or ??? |  |  | 0.5 | 3 | 4500
Column totals | 0.5 | 0.5 | 15 | 3
Total total (days) | 19
$$$ Total |  |  |  |  | 28000