## Sheet1
| Gene | Users | Jon | Jim S. | Mark G. | $$$ Costs
Pick a preferred design | 1 | 0.5
Final FEA work | 5 |  | 3
Optimize W/D ratio and weight in water |  |  |  |  | 2
Fix local high stress areas |  |  |  |  | 2
Make sure connector bores don’t distort unacceptably for proper sealing |  |  |  |  | 1
Re-do FEA with outer O-ring failure |  |  |  |  | 1
Equalize bearing pressure at dual O-ring grooves |  |  |  |  | 1
Check calcs
Generate drawingsGenerate model drawings & check | 2 |  | 4 |  | 2.5
Generate model drawings & check
Work with Oremet Wah-Chang (and Jon) to optimize manufacturability
Generate as cast drawings & check
Generate "as Machined" drawings
Buy 1
Patterns | [5 empty] | 5000
Casting | [5 empty] | 6500
Machining | [5 empty] | 12000 | This is a bit of a guess but the last set of halves cost $7400 each @ Tapemation, these should require somewhat less machining
Pressure test at Pt. Hueneme or ??? | 0.5 |  |  | 3 | 1 | 4500
Column totals | 8.5 | 0.5 | 7 | 3
Total total (days) | 19
Mark G ($100/hr) |  |  |  |  | 10.5 | 8400
Estimated cost for 1 sphere w/Mark G finishing design | [5 empty] | 36400