## Slide 1: CANON Fall Experiment
Draft questions and plans

## Slide 2: Science Questions/Objectives
What are the source waters and seed populations for phytoplankton blooms in and out of Monterey Bay?
What are the processes responsible for phytoplankton blooms or lack thereof in and outside of Monterey Bay?
What are the biogeochemical consequences (particulate flux, nutrient regeneration) of phytoplankton blooms or lack thereof in and outside of Monterey Bay?

## Slide 3: Technical questions/objectives
Can we identify and trace source water and seed populations for phytoplankton blooms in and out of Monterey Bay?
Can we develop environmental indices that can be used to predict the location and timing of blooms with enough accuracy and speed to be used to trigger autonomous sampling?
Can we develop an information processing and display system that can be used in real time to improve decision making and publication preparation in delayed mode?

## Slide 4: Operational Plan
Repeatedly (10 or more times during the course of the month?) deploy drifters and LST along Line B or equivalent. The offshore pair would be occasionally in high chl offshore, the middle in high flow, low chl, the inshore (drifter only, too shallow for LST) in low flow, high chl in association with the ESPs. The drifters would have water collected at the site of deployment and changes in the bottles will be monitored over 1-3 days. The AUVs and ships would follow the drifters and LSTs collecting information in situ for comparison with those contained in bottles on the drifters. Gliders would run fixed grids except for Tex that would follow LSTs to provide location information to shore for navigating the ships and AUVs.

## Slide 5
Chavez et al.
2006

## Slide 6
Pennington et al. (2009)

## Slide 7: Ships
Western Flyer – PCTD, UCTD, profiling pump, optics
Rachel Carson - PCTD, UCTD, profiling pump, optics
Paragon – LST, Glider, drifter support
Martin – ECOHAB, PCTD, UCTD, optics
Fulmar (?) - PCTD, UCTD, optics

## Slide 8: AUVs
Dorado
Tethys
Daphne
U of Porto ?
Other ?

## Slide 9: Gliders
Spray Line 67
Spray NPS
Spray NPS
Slocum Teledyne
Slocum UCSC
Slocum UCSC
WG OA
WG Tex

## Slide 10: Moorings
M1
M2H
OA1
OA2
ESP 1
ESP 2
Other ?

## Slide 11: LST, drifter, other
LST (= Lagrangian sediment trap) 1
LST 2
Stella 1-n (what is n?)
Android 1-n
Floats ?
ROMS-NPZD 3 km
Remote sensing (standard, Hyspiri, drone?)
Cowen zoo system ?
Flocam?
ADCPs?
Geostrophy?

## Slide 12
Chavez
Ryan

## Slide 13
67-60
67-65
67-55
OA2
OA1
ESP2
ESP1
ESP2?
LST1
LST2
LRAUV
Wave Glider
Dorado
WEBB Glider
Spray Glider
Rachel Carson
Western Flyer
Mooring
Drifter
LST
Martin
Paragon
√

## Slide 14: Working groups and leads (members in parentheses)
Science planning – Ryan (Bellingham, Chavez, Scholin, etc.)
Logistics – Maughan (Edgington, Rajan, Chavez, etc.) - timeline
Autonomous mobile platforms – Bellingham (Wahl, Ryan, Zhang etc.) – can/should we use Dorado in between Carson cruises
Autonomous drifting platforms – Smith (Sherman, Chavez, Wahl, etc.) – what are the issues with LSTs
Data analysis – Messie (Ryan, McCann, Bellingham, Chavez, etc.) – standard products, user interfaces, models, etc.
Samples – Pennington (Blum, Smith3, Kudela, Preston, Zhang, etc.) – inventory, gaps, etc.
Data management – Gomes/Michisaki – what is it?
Responsibility of lead to develop a list (questions, platforms, products, data, samples), a means to answer/produce/distribute, analysis, organize team, etc.

## Slide 15
SAMPLES WORKING GROUP
1. Operational definition of sample: A physically-collected sample, as distinct from an electronically-collected datum.
2. Purpose:
Provide some coordination for the taking of samples by the different platforms and research groups --- goal of insuring complete datasets are obtained
Budget water and effort
Document responsibilites
Document sample collection, processing and data flow
Interface with Data Management and Analysis
3. Platforms and routine samples:
CTD rosette Niskin bottles:
-Depths: 0,0, 5, 10, 20, 30, 40, 60, 80, 100, 150, 200m
-Profiles: Macronuts, ammonium, chl, C14-PP, ?triplepoint-PP
-Surface: POC, HPLC, FCM, A*, QP, 5&1um Chl and C14-PP
-Additional: Winkler oxygen, salt, DIC/TCO2, ALK, N03&NH4-PP
Profiling pumped CTD -???
AUV Gulpers -???
ESP -???
Drifting sediment traps -???
Drifting productivity arrays -0, 5, 10, 20, 30, 40m
-C14-PP, NO3&NH4PP, O2-PP, final macronuts and NH4, POC, QP
Other …

## Slide 16: Practice makes perfect
WG go through the September 2012 ESP tracking experiment
Out the other end a series of papers!
Exploring a Special Issue
The canon@mbari.org mailing list has been culled for the present experiment, need to make sure those involved are on the list, other means of communication being explored

## Slide 17: Preparatory analysis
Remote sensing, models, in situ data from September and domain

## Slide 19
Platforms (AUVs, Ships, Bottles, etc.
Gridded data
Satellite, models, etc.
SQL data, netcdf, ASCII, etc.
Information Management
Planning
Situational awareness
Data analysis (e.g. Matlab, STOQS UI)
Collaborative workspace
ODSS
Samples?