CANON June Experiment

Straw-plan draft, 6 June 2011

1. Research focus: pelagic ecosystem dynamics across frontal boundaries

Oceanic fronts shape coastal marine ecology.  They define boundaries between water masses that have distinguishing environmental attributes and biological populations.  The dynamics of fronts create interactions between water masses and influence pelagic ecology in a variety of ways.  At the core of the food web, frontal dynamics can enrich growth conditions, aggregate and transport blooms, cause formation of concentrated biological layers, and couple the bottom and surface boundary layers.  Aggregation of biogenic surfactants at fronts has also been linked to a recently discovered mechanism by which certain harmful algal blooms (HABs) damage marine life.  In addition to supporting enriched phytoplankton populations as energy for zooplankton, fronts may influence zooplankton ecology through population aggregation as well as transport patterns that determine the scales and geography of larval dispersal and recruitment.  At further reaches of the food web, the ecological significance of fronts is evident in the aggregation of foraging seabirds, marine mammals, and human fishing activities.

The Monterey Bay primary upwelling source, Point Año Nuevo, and its upwelling shadow in the northern recess of the bay, together form a system that hosts recurring creation and dynamic evolution of fronts.  This system also creates a natural patch-tracking laboratory.  The upwelling filament - shadow frontal zone became a focus during the April 2011 CANON experiment, not only because of its ecological significance, but also because of its accessibility and its substantial problem presentation to advancement of observing technologies and techniques.  Integrating lessons learned from the April experiment with tested and newly developed AUV capabilities, a key goal of the June experiment is to advance interdisciplinary study of this dynamic frontal zone.

Considering a lesson learned in April, we will more closely coordinate ship-based and AUV observing resources along a single transect in June, similar to the Tethys and Dorado frontal sections north of M0 at the end of the April experiment.  This closer coordination is intended to support a high-resolution time-series at a consistent location that is in the ocean-transport pathways of circulation forced by both upwelling and relaxation / downwelling. With all observations coordinated along this slice of ocean, we will be able to drill more deeply into understanding ecosystem properties, processes and plankton, and we will capture events and their interludes.

For scientific and system-development goals, a fixed transect would be well placed where we are likely to see strong gradients in physical and biological conditions.  Long-term mean conditions for June can inform placement of a focal transect for the CANON June experiment.  Shown in Figure 1 are average SST, the zonal gradient of average SST, and average chlorophyll fluorescence line height (FLH).  These mean patterns show that the physical and biological gradients of the upwelling filament / upwelling shadow complex are greatest, on average, toward the northern end of the bay.  For example, a fixed zonal section along 36.9ºN would presumably provide a relatively high probability of encountering strong frontal gradients – in support of science and testing of autonomous response to frontal systems.  Patch tracking from the outer northern bay frontal zone would also likely define trajectories that lead into the bay (rather than offshore).  The placement of this transect, toward the northern end of the bay (but south of kelp beds that could entangle AUVs) will effectively focus research on the upwelling response and variability.  However, bay flushing events (observed by satellites and drifters) also indicate that this transect placement would effectively resolve rapid changes that can occur during strong wind relaxations and reversals.  Other fixed transect locations can be considered from the perspectives of science, engineering and operational goals.

Figure 1.  Average June SST, its zonal gradient, and average summer (May-July) chlorophyll fluorescence line height (proxy for phytoplankton abundance).

2. Scales of observation

A regional view is essential, and satellite remote sensing of sea surface temperature (SST) will support this view to some degree.  For this experiment, “regional” means Monterey Bay and adjacent upwelling centers (primarily Point Año Nuevo).  To maximize the potential to see regional SST patterns that inform our operations (when clouds and fog are not blocking the view), we will use an optimally processed SST data set.  Availability of this data through ODSS is being established.  However, even with good satellite SST data, we may have periods when visibility remains blocked for extended periods.  As for April, the R/V Martin will serve a key role in providing a subset of regional perspective (northern bay), regardless of visibility by satellite remote sensing.  The Martin will provide line-of-transit maps of near-surface properties to describe multidisciplinary detail of water types and fronts.  Also, integrated data from the MBARI moorings will support understanding at the regional scale (in addition to the local scale of their point on the map).

The next smaller scales we can identify for planning are those focused on in situ observation across adjacent water types and their front, and that of patch tracking.  These scales are ~10-30 km horizontal (the fixed transect shown in Figure 1 is 30 km), within the upper 100 m.  The platforms focused on this scale will include the R/V Martin, AUVs, and possibly drifters (released on the inshore side of the upwelling shadow front, to evaluate convergence).  In addition to surface underway mapping, the R/V Martin will support targeted deployment of the profiling CTD, with water sample acquisition.  Both the AUV Gulper and Martin CTD water sampling capacity will be focused on sampling in adjacent water types and the front between them.  The Martin will have the added advantage of sampling closer to the surface, where larvae and other zooplankton may aggregate. The coordinated Tethys / Dorado operations during April proved to be an effective integration of capabilities, with Tethys locating the front, passing this information to Dorado, and Dorado mapping and sampling across the front.  It may be effective to build on this success during the June experiment.

The next smaller scale to consider is the local vertical scale (meters).  Previous molecular results from Dorado / Gulper sampling indicate that targeting sampling (including controls) relative to local peaks in chlorophyll fluorescence is an effective way to find locally enhanced zooplankton populations.  It is also consistent with the CANON goal of examining trophic linkages.  Vertical sampling according to local vertical structure makes sense for the upwelling shadow waters, which are relatively mature in terms of plankton community growth.  However, it does not make sense for recently upwelled waters, which have comparatively little vertical structure in phytoplankton abundance.  A method for appropriately targeting Gulper sampling in upwelling shadow, filament and frontal locations has been prepared based on observations from the April experiment, and it is ready to be tested on Dorado.  We also have another method developed for TREX frontal tracking.  If the Martin has real-time viewing of vertical structure from the profiling CTD, we can consider similar targeting of local phytoplankton peaks in the upwelling shadow, as well as near-surface sampling at the very narrow convergence zones that can develop within the greater (complex) upwelling frontal zone.

3. Experiment plan

Week of June 6

Satellite and mooring data analysis will begin, to inform Tethys operations and to prepare for the larger field effort to begin the following week.  In situ operations will include only Tethys.  In addition to core goals of the Tethys team (engineering and science), information about water mass and frontal conditions provided by Tethys will inform our preparations for multi-platform in situ observations the following week.

Week of June 13

This is the first week of integrated observations by both AUVs and the Martin.  We have goals of transferring Martin data (plots of underway mapping system) to shore, to help inform the 10 am planning meeting.  Does the location of the transect across the northern bay introduce too much transit time to complete a run across it with the Martin in time for transfer to the 10 am meeting?  Dorado days are scheduled for June 13 – 16; these are Rajan / T-REX days.  If Tethys operations are focused in northern bay along the fixed transect, monitoring the front and its variability, then an effective observing strategy may be to apply the well-developed frontal detection algorithm of Tethys to define a frontal position for Dorado missions.  Unlike April, we will not want Dorado to survey a box at the frontal location last reported by Tethys.  Instead, we will have Dorado mapping along the focal transect, using its “heavier” payload for targeted observation and sampling.  For example, if we can prescribe the longitudes of the Dorado repeat-section endpoints as ± 5 km from the frontal location passed from Tethys, we could optimize the opportunities for autonomously targeted Gulper sampling in the adjacent water types and their front.  If Tethys is patch tracking, we could maintain a repeat section across the front, informed by available satellite and Martin underway data. When Dorado is mapping frontal zones, Gulper control will be focused on getting samples within and on either side of the front, consistently, for molecular analyses.

Week of June 20

Coordination of Tethys, Dorado and the Martin will be possible only during the first 3 days of this week.  The Tethys team is currently planning to focus on patch tracking this week.  In this case, options for effective integrated application of capabilities may include:

- Start Tethys patch-tracking in the northwestern bay, near the upwelling shadow transect (if an appropriate patch is found near there), and apply coordination of Martin and Dorado operations to maintain a focused effort across the frontal zone, as well as monitoring the source region of the patch that is being tracked by Tethys.

- Let Dorado follow Tethys during patch tracking (ala October 2010 CANON experiment), applying its augmented sensing and Gulper sampling.  Although this might dilute the primary goal of maintaining a focus along the fixed transect, perhaps Dorado could run the northern section once (with Gulper sampling) before proceeding to follow Tethys’ patch tracking.